## Description of Project
Description of the Project
HealthHub is a cutting-edge healthcare platform that transforms interactions with healthcare providers and the management of personal well-being. It offers individualized health assessments with insights and proactive recommendations based on consumers' needs, utilizing advanced analytics and machine learning. Its telehealth function makes it easier to have virtual consultations with medical specialists, promising fast service delivery. For thorough health monitoring, users can connect data from wearable devices, track medication adherence, and securely maintain medical records. While AI-driven forecasts indicate possible health hazards for preemptive action, interactive challenges and rewards encourage healthy lifestyles.

## Versions
1. Version 1 | Responsibles | Release Date of Versions
Login With pasword (v1.0) | Talha Shahzad | v1.0 - 17.3.2024
Keeping member records (v1.0) | Talha Shahzad | v1.0 - 18.3.2024
Keeping personnel information (v1.1) | Talha Shahzad | v1.0 - 19.3.2024
2. Version 2 | Responsibles | Release Date of Versions
Risk Analysis (v2.0) | Talha Shahzad and Husnain Ali | v2.0 - 20.3.2024
Personal Insights (2.0) | Talha Shahzad and Husnain Ali | v2.0 - 21.3.2024
Get Recommendations (2.1) | Talha Shahzad and Husnain Ali | v2.0 - 25.3.2024
Review past journey (v2.1) | Talha Shahzad and Husnain Ali | v2.0 - 26.3.2024
3. Version 3 | Responsibles | Release Date of Versions
Remote device integration (v3.0) | Ali Khizar | v3.0 - 27.03.2024
Test Result Accessibility (v3.1) | Ali Khizar | v3.1 - 28.03.2024
Report (v.1) | Ali Khizar | v3.1 - 28.03.2024

## Product Backlog
Product Backlog
User Stories
Situation | Name | Description | Point
Done
Done
Done
Done
Done
Done
Done
Done
Done
Done
It is cancelled

## BurnDown
BURNDOWN CHART Sprint 1
Project | Story | Beginning | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03
HealthHub | Login with Password | 12 | 8 | 4 | 4 | 4 | 2 | 3 | 2 | 2 | 1 | 0
HealthHub | Health Assessment | 15 | 12 | 10 | 8 | 6 | 2 | 3 | 2 | 2 | 1 | 0
HealthHub | Consultation Schedule | 9 | 4 | 8 | 8 | 12 | 2 | 1 | 2 | 5 | 1 | 0
HealthHub | Virtual Consultation | 7 | 8 | 12 | 8 | 2 | 8 | 3 | 3 | 2 | 1 | 0
HealthHub | Wellness Chanlleges | 3 | 8 | 3 | 4 | 3 | 8 | 0 | 5 | 1 | 3 | 0
0
0
0
0
0
Ideal - Remaining time working hours |  | 46 | 41.4 | 36.8 | 32.2 | 27.6 | 23 | 18.4 | 13.8 | 9.2 | 4.6 | 0
Actual - Remaining time working hours |  | 46 | 40 | 37 | 32 | 27 | 22 | 10 | 14 | 12 | 7 | 0